## Sheet1
Job | Start date | Duration | Person
Get a team together | 2011-09-23 | 1 | Both
Decide on assignment topic | 2011-10-02 | 1 | Both
Start actionscript | 2011-10-03 | 60 | Matt
Choose the units and their stats | 2011-10-05 | 5 | Both
Make graphics | 2011-10-05 | 60 | Ruby
Make Gantt chart | 2011-10-05 | 1 | Matt
Implement various features | 2011-10-20 | 10 | Both
Get assignment | 2011-10-25 | 1 | Both
Various bits of documentation | 2011-11-02 | 3 | Both
Add menus | 2011-11-05 | 5 | Both
Add cutscene | 2011-11-10 | 10 | Both
Do advanced features | 2011-11-15 | 7 | Both
Evaluation | 2011-11-20 | 1 | Both